## CRONOGRAMA
CRONOGRAMA DE ACTIVIDADES
Desglose		ACTIVIDADES	RECURSOS				SEMANAS
					SEMANA 1					SEMANA 2					SEMANA 3					SEMANA 4
			LG	FG	JH	MV	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20
1	1	Módulo link	x
1	2	Game: callback move	x
1	3	Game: callback inspect	x
2	1	Graphic_engine: objects name		x
2	2	Graphic_engine: links		x
2	3	Graphic_engine: inspect/description		x
2	4	Game: link		x
3	1	Módulo inventory			x
3	2	Player: inventory			x
3	3	Game: callbacks take y drop			x
4	1	Game_reader: load player				x
4	2	Game_reader: links				x
4	3	data.dat				x
5	1	Depuración			x	x
5	2	Diagrama de Gantt: revisión	x	x
5	3	Comprobar pruebas	x	x	x	x
5	4	Tests de software	x	x	x	x
5	5	Últimos retoques	x	x	x	x

## RECURSOS
IDENTIFICACIÓN DE RECURSOS
R1	Nombre1
R2	Nombre2
R3	Nombre3
R4	Nombre4
R5	Nombre5
R6	Nombre6